## WBS
Work Breakdown Structure | [5 empty] | Knowledge Space
© 2017 by Vertex42.com
| Project Start | 2023-04-21 |  |  |  |  | Work Breakdown Structure
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Design and analysis |  |  |  |  | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 1.1 | Collecting requirement | Hung
2 | 1.2 | Analyis requirement | Hung
2 | 1.3 | Create user stories | Hung
2 | 1.4 | Design solution architecture | Hung
2 | 1.5 | Design functions | Hung
2 | 1.6 | Design database structure | Hung
1 | 2 | Technical preparation | Hung
2 | 2.1 | Setup development environment | Hung
2 | 2.2 | Setup test environent | Hung
2 | 2.3 | Create Git repository | Hung
2 | 2.4 | Create source code structure | Hung
1 | 3 | Implement Backend API | Hung
2 | 3.1 | Create entity classes | Hung
2 | 3.2 | Configure entity classes using Fluent API | Hung
2 | 3.3 | Configure Entity Framework Core | Hung
2 | 3.4 | Configure ASP.NET Core Identity | Hung
2 | 3.5 | Generate to Database | Hung
2 | 3.6 | Configure Identity Server | Hung
2 | 3.7 | Scaffold Identity UI | Hung
2 | 3.8 | Install Swagger | Hung
2 | 3.9 | Config swagger to accept authentication | Hung
2 | 3.10 | Customize Identity Server for Authentication | Hung
2 | 3.11 | Implement Role APIs | Hung
2 | 3.12 | Add Fluent Validation | Hung
2 | 3.13 | Add Unit tests | Hung
2 | 3.14 | Implement User APIs | Hung
2 | 3.15 | Implement function APIs | Hung
2 | 3.16 | Implement permission APIs | Hung
2 | 3.17 | Implement action Apis | Hung
2 | 3.18 | Implement ticket APIs | Hung
2 | 3.19 | Implement comment APIs | Hung
2 | 3.20 | Implement Vote APIs | Hung
2 | 3.21 | Implement Ticket Category APIs | Hung
2 | 3.22 | Implement report Apis | Hung
2 | 3.23 | Implement dashboard Apis | Hung
2 | 3.24 | Apply permission to APIs | Hung
1 | 4 | Implement Admin Angular | Hung
2 | 4.1 | Create Angular project | Hung
2 | 4.2 | Create structure solution | Hung
2 | 4.3 | Add template | Hung
2 | 4.4 | Integrate login with Identity Server | Hung
2 | 4.5 | Create common service | Hung
2 | 4.6 | Create login page | Hung
2 | 4.7 | Create menu | Hung
2 | 4.8 | Config permission for menu | Hung
2 | 4.9 | Create role page | Hung
2 | 4.10 | Create user page | Hung
2 | 4.11 | Create permission page | Hung
2 | 4.12 | Create function page | Hung
2 | 4.13 | Create ticket category page | Hung
2 | 4.14 | Create ticket page | Hung
2 | 4.15 | Create comment page | Hung
2 | 4.16 | Create report page | Hung
2 | 4.17 | Create dashboard page | Hung
1 | 5 | Implement Web portal | Hung
2 | 5.1 | Create Web portal structure | Hung
2 | 5.2 | Integrate with Identity Server | Hung
2 | 5.3 | Add layout template | Hung
2 | 5.4 | Integrate with Backend API common | Hung
2 | 5.5 | Create home page | Hung
2 | 5.6 | Create ticket list page | Hung
2 | 5.7 | Create ticket detail page | Hung
2 | 5.8 | Comment for ticket | Hung
2 | 5.9 | Vote for ticket | Hung
2 | 5.10 | Report for ticket | Hung
2 | 5.11 | Profile page | Hung
2 | 5.12 | Update profile page | Hung
2 | 5.13 | Change password page | Hung
2 | 5.14 | List ticket by user | Hung
2 | 5.15 | Create new ticket | Hung
2 | 5.16 | Notification SignalR | Hung
1 | 6 | UAT | Hung
1 | 7 | Deploy to production | Hung
◄ Add new rows ABOVE this one.

## Help
HELP
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html |  | © 2017 Vertex42 LLC
About this Template
This template provides a very basic WBS table that you can use for defining a hierarchical work breakdown structure for a project plan or process.
Want more features and automation?
Try the Gantt Chart Template by Vertex42.com
Note: The formula for the WBS numbering was developed by Vertex42.com for the Gantt Chart Template Pro spreadsheet, and is copyrighted. See the terms of use.
Instructions
1) | Choose a Level from the drop-down list in column B. The WBS code is created automatically. When adding rows, you will need to copy the formula in the WBS code column into the newly added rows.
2) | Indent Task Descriptions using the Indent buttons in the Home tab.
3) | Add or hide columns as needed.
4) | A conditional formatting rule automatically highlights level 1 tasks. Go to Home > Conditional Formatting > Manage Rules to remove or edit this rule.
Terms of Use
See the following page for information about how you may use this spreadsheet.
https://www.vertex42.com/licensing/EULA_privateuse.html
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Work Breakdown Structure
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.